## Project Backlog
Tasks for Renderer | Story Points | Status | Finished
Set up Repo | 5 |  | In Progress
Implement window | 30 |  | Not Started
Implement graphics context | 5
Draw a quad | 7
Draw a quad with PVP | 15
Draw a textured quad with PVP | 12
Implement quads and camera | 4
Implement scene | 50
Write renderer API | 3
Implement Renderer Ctor Shader | 10
Implement Renderer Ctor SSBO | 9
Implement Renderer Ctor UBO | 9
Implement Renderer Ctor VAO | 9
Implement Renderer Dstor | 3
Implement begin() | 25
Implement flush() | 25
Implement end() | 10

## Velocity
Date | Week | SP | SP Remaining | Velocity | 21
2026-02-26 | -7 | 5 | 226 | Weeks | 11
2026-03-05 | -6 | 35 | 191
2026-03-12 | -5 | 0 | 191
2026-03-19 | -4 | 0 | 191
2026-03-26 | -3 | 7 | 184
2026-04-02 | -2 | 18 | 166
2026-04-09 | -1 | 0 | 166
2026-04-16 | 0 | 10 | 156
2026-04-23 | 1 | 12 | 144
2026-04-30 | 2 | 137 | 7
2026-05-07 | 3 | 7 | 0
2026-05-14 | 4 |  | 0
2026-05-21 | 5 |  | 0
2026-05-28 | 6 |  | 0

## Continuous Testing
Date | Item | Test case | Passed? | Notes
5th Mar 2026 | Implement window | Does the window open? | Pass | No changes needed.
| Implement window | Does the window close? | Pass | No changes needed.
9th Mar 2026 | Implement graphics context | Is there GLFW context | Fail | Thought it was, however my order was wrong. Change order and add cout to confirm.
| Implement graphics context | Is there GLFW context | Pass | No changes needed.
26th Mar 2026 | Draw a quad | Does a quad render? | Pass | Renders but is entire screen and flickers. Change vertex datawhere function is being called.
| Draw a quad | Does a quad render? | Pass | No changes needed.
2nd Apr 2026 | Draw a quad with PVP | Does quad render with SSBOs? | Fail | No errors but blank screen.
| Draw a quad with PVP | Is the vertex data passed to GPU | Pass | No changes needed.
| Draw a quad with PVP | Does the quad render with SSBOs? | Pass | Vertex struct needed padding as data was being read incorrectly due to std430 works.
3rd Apr 2026 | Implement quads and camera | Are camera uniforms correctly setup? | Pass | No changes needed.
| Implement quads and camera | Are camera uniforms correctly setup? | Fail | Was never multiplying the by the view projection matrix in vertex shader. Need to fix the matrix's.
9th Apr 2026 | Draw a textured quad with PVP | Is texture correctly created? | Pass | No changes needed.
10th Apr 2026 | Draw a textured quad with PVP | Does textured quad renderer? | Pass | Not sure why, need to investigate.
21st Apr 2026 | Implement Renderer Ctor Shader | Does CompileShader() function work? | Pass | No changes needed.
| Draw a textured quad with PVP | Is texture handle carried over to GPU | Fail | Doesn’t seem to ever read from SSBO containing texture handles.
23rd Apr 2026 | Draw a textured quad with PVP | Is texture handle carried over to GPU | Pass | Texture handle wasn't being made resident.
| Draw a textured quad with PVP | Does texture render correctly? | Fail | Texture renders but I think UVs are wrong.
| Draw a textured quad with PVP | Does texture render correctly? | Pass | Fixed issue with Uvs, texture now renders without issue.
27th Apr 2026 | Draw a textured quad with PVP | Is texure being created properly using function rather than hard-coded? | Pass | No changes needed.
| Draw a textured quad with PVP | Is texture handle created properly with function rather than hard-coded? | Pass | No changes needed.
| Implement scene | Do the render components hold correct data? | Fail | Break point isn't triggered so may not be getting called correctly.
28th Apr 2026 | Implement quads and camera | Does the quad render when multiplied by view projection matrix? | Fail | Quad disappears after multiplying model by projection and view.
| Write renderer API | Is Renderer called by the scene? | Pass | No changes needed.
| Write renderer API | Does renderer render textured quad? | Fail | Crashes with dereferencing error, need to investigate.
29th Apr 2026 | Draw a textured quad with PVP | Does texure render when using flat int for multiple texture handles? | Pass | No changes needed.
| Write renderer API | Is the renderer correctly initialised and rendering? | Pass | Correctly initialises and renders but currently only backgroud culour and flickers.
| Write renderer API | Is onRender reading data from scene and rendering correctly? | Pass | Scene renderers with quad but still flickers.
6th May 2026 | Implement scene | Are multiple quads rendering? | Fail | Not working because its not taking into account multiple instances in vertex shader.
| Implement scene | Are multiple quads rendering? | Pass | Quads rendering after adding index to vertex shader.
11th May 2026 | Implement window | Is the window resizeable? | Fail | Though a fail, its the desired outcome. No changes needed.
13th May 2026 | Implement scene | Does transform component rotate quad? | Pass | Quad rotates but seems to be sheering. Need to diagnose the problem.
| Implement scene | Does transform component scale quad? | Pass | No changes needed.
| Implement scene | Does transform component translate quad? | Fail | Translation seems to never be updating in the transformation matrix.
14th May 2026 | Implement scene | Does transform component translate quad? | Pass | Had to manually construct the translation matrix but it all works.
| Implement quads and camera | Do quads render when multiplied by vp matrix? | Pass | Renders but is currently multiplied by identity matrix which caused sheering.
19th May 2026 | Implement quads and camera | Do quads render when multiplied by vp matrix? | Pass | Renders as quads without sheering as projection matrix is now correctly implemented.
29th May 2026 | Draw a textured quad with PVP | Does renderer construct quad UVs correctly? | Fail | Current UVs removed chequered pattern of testing texting. Only rendered flat colour. Fixed by hardcoding UVs and changing UV construction based on that.
30th May 2026 | Draw a textured quad with PVP | Does quad render correctly with fixed UV construction? | Fail | Rendered upside down due to incorrect winding order.
| Draw a textured quad with PVP | Does quad render correctly with correct winding order? | Pass | No changes needed.

## Whitebox Testing
Renderer Whitebox Testing
Date | Test Case | Expected outcome (Pass/Fail) | Actual Outcome | Evidence
19th May 2026 | Vertex positions match the calculated rotations | Pass | Pass | x | y | th | 0.70711 | -0.70711 | 0 | Expected Values |  | Values on CPU
|  |  |  | -0.175 | -0.2 | 45 | 0.70711 | 0.70711 | 0 | -0.26517 | -0.017678 | -0.26517 | -0.01768
|  |  |  | -0.175 | 0.2 |  | 0 | 0 | 1 | 0.017678 | 0.26517 | 0.017678 | 0.26516
|  |  |  | 0.175 | -0.2 |  |  |  |  | -0.017678 | -0.26517 | -0.01768 | 0.26517
|  |  |  | 0.175 | 0.2 |  |  |  |  | 0.26517 | 0.017678 | 0.26516 | 0.017678
21st May 2026 | Alignment of classes and structs - Renderer class | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - Vertex Struct | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - TextureDescription Struct | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - WindowProperties Struct | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - Window Class | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - InputSystem Class | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - Camera Struct | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - Application Class | Pass | Fail | See alignment table for evidence.
| Alignment of classes and structs - RenderComponent Struct | Pass | Pass | See alignment table for evidence.
| Alignment of classes and structs - TransformComponent Struct | Pass | Pass | See alignment table for evidence.

## Alignment Table
Class | Struct | Alignment | Before | After
Renderer |  | Already Aligned | #VALUE!
| Vertex | Already Aligned | #VALUE!
| TextureDescription | Already Aligned | #VALUE!
| WindowProperties | Already Aligned | #VALUE!
Window |  | Already Aligned | #VALUE!
InputSystem |  | Already Aligned | #VALUE!
| Camera | Already Aligned | #VALUE!
Application |  | Needs Aligning | #VALUE! | #VALUE!
| RenderComponent | Already Aligned | #VALUE!
| TransformComponent | Already Aligned | #VALUE!